## Sheet1
Task ID | Category | Task Name | Description | Priority | Estimated Days | Owner | Status
3.1 | SKU Splitting | Trend Analysis | Analyze historical share trends for key SPUs to validate hypothesis | High | 1 | DS | Pending
3.2 | SKU Splitting | Algo Implementation | Develop TrendWeightedShare logic to replace static mean | High | 2 | Dev | Pending
3.3 | SKU Splitting | Normalization | Implement Softmax/Normalization to ensure sum=1 | Medium | 1 | Dev | Pending
3.4 | SKU Splitting | Backtesting | Run A/B test on validation set (New vs Old) | High | 2 | DS | Pending
4.1 | Automation | Script Hardening | Finalize env var config and error handling in main.py | Medium | 1 | Dev | Pending
4.2 | Automation | Scheduler Setup | Create Windows Task Scheduler script (.bat) or Python Scheduler | High | 1 | Ops | Pending
4.3 | Automation | Alerting System | Build monitor to check WMAPE > 30% and trigger alert | Medium | 2 | Dev | Pending
4.4 | Automation | Dashboard Update | Update SQL views to support trend analysis | Low | 1 | BI | Pending